CHEF'S OFFICE

2-Week Operational Action Plan

Antonio & Sean  |  Phase 1 Execution  |  Confidential

Context & Objectives

This plan covers the first two weeks of engagement with Chef's Office Academy (Ricardo Calderini, Perth). It defines the specific actions, owners, and sequence required to deliver Phase 1 of the signed engagement agreement.

Brand: Chef's Office Australia — Executive Academy

Mission: Help chefs transition from skilled cooks to confident kitchen leaders and business-minded professionals.

Brand tone: authority, clarity, real-world experience. Professional academy — not lifestyle content, not hype.

90-Day contract goals:

- Stable tracking and campaign infrastructure

- Consistent acquisition cost benchmark established

- AI for Chefs digital product launched and integrated into funnel

- Demand generated for Chef's Office cohort program

- 10 cohort enrolment spots filled by months 2-3

These first two weeks are infrastructure-first. No campaigns launch until tracking is verified and creative is ready.

Responsibility Split

Work is divided 50/50. Each owns distinct lanes — no duplication, no gaps.

| ANTONIO | SEAN |
| --- | --- |
| Funnel strategy & architecture Creative strategy & ad briefs Offer positioning & copy Upsell flow design & page briefs Email sequence strategy & copy | Meta Ads account audit & restructure Pixel setup & conversion event verification Tracking stack review (GA4, UTMs) Campaign structure & audience research Reporting template & client comms |

Week 1 — Foundation & Audit (Days 1–7)

Priority: understand the current state before building anything new. No campaigns, no creative spend. Fix the infrastructure first.

| Day | Owner | Task | Notes |
| --- | --- | --- | --- |
| Day 1–2 | Antonio | Map full funnel architecture: traffic to ascension | Books > Modules > Certification > Membership > Mentorship — align with brand value ladder |
| Day 1–2 | Sean | Meta Ads account audit: existing campaigns, ad sets, audiences | Document what exists, what's broken, what to cut |
| Day 2–3 | Antonio | Audit AI for Chefs product: positioning, pricing, page copy | Is offer strong enough to drive cold traffic? Flag gaps |
| Day 2–3 | Sean | Pixel audit: verify all conversion events fire on checkout + thank you pages | No campaigns until this is confirmed clean |
| Day 3–4 | Antonio | Brand alignment audit: review all existing assets against Chef's Office brand guidelines | Navy #1F2A44 ¦ Gold #C7A86D ¦ Authority tone — no hype, no lifestyle |
| Day 3–4 | Sean | Tracking stack: GA4 setup, UTM parameter framework, naming conventions | Build the attribution layer before spend starts |
| Day 4–5 | Antonio | Identify creative angles: 3–5 ad hook concepts for hospitality audience | Ref brand guideline: 'Most chefs never learn food cost. That's why kitchens fail.' — direct, educational, credible |
| Day 4–5 | Sean | Audience research: interest stacks, lookalike seed lists, cold audience plan on Meta | Hospitality professionals AU — chefs, kitchen leaders, culinary students |
| Day 5–6 | Antonio | Design upsell sequence flow: OTO 1 ($14.97), OTO 2 ($19.97) — page structure briefs | Logic: buy front-end > immediate upsell > second upsell > email nurture |
| Day 5–6 | Sean | Restructure Meta Ads account: campaign naming, campaign objective selection, ad set structure | Brand campaign + cold acquisition campaign + retargeting — separate budgets |
| Day 7 | Both | Week 1 sync with Ricardo — present audit findings, confirm direction, agree on Week 2 priorities | Keep it direct. Show what exists, what changes, what launches in week 2 |

Week 2 — Build & Pre-Launch Preparation (Days 8–14)

Priority: build the assets needed to launch. Everything Sean builds needs Antonio's creative to be ready. Sequence matters.

| Day | Owner | Task | Notes |
| --- | --- | --- | --- |
| Day 8–9 | Antonio | Write landing page copy: AI for Chefs front-end offer ($9.97) | Tone: authority + practical value. No hype. Lead with outcome: 'What every chef needs to know about running a kitchen efficiently.' |
| Day 8–9 | Sean | Build campaign structure in Meta Ads: cold audience + retargeting shells ready to activate | Hold budget until creative is approved and pixel is verified |
| Day 9–10 | Antonio | Write ad copy: 3 headline + body variants per creative angle | Ref brand: educational short-form, founder-led, carousel with practical lessons |
| Day 9–10 | Sean | Implement UTM parameters across all funnel URLs | Every traffic source tagged before first dollar of spend |
| Day 10–11 | Antonio | Write OTO 1 and OTO 2 page copy (upsell sequence) | Brief copywriter or write direct — needs to be complete before funnel test |
| Day 10–11 | Sean | Set up performance reporting dashboard: CPL, CPA, ROAS, upsell attach rate | Weekly report template for Ricardo — clean, commentary-driven, no jargon |
| Day 11–12 | Antonio | Draft email welcome sequence: 5 emails (buy confirmation > value delivery > cohort invitation) | Tone: professional, practical, direct. Ricardo's voice. No soft fluff. |
| Day 11–12 | Sean | Funnel flow test: end-to-end purchase, upsell trigger, thank you page, pixel fire confirmation | Every step must work before campaigns activate |
| Day 12–13 | Antonio | Creative review with Ricardo: walk through ad angles, copy variants, brand alignment | Get sign-off on creative direction before production. Flag any misalignments with brand guidelines. |
| Day 12–13 | Sean | Final pre-launch checklist: pixel, tracking, budget allocation, campaign objectives confirmed | Document every item. No assumptions. |
| Day 13–14 | Antonio | Finalise AI for Chefs product integration brief: funnel pages, email trigger, upsell logic | Hand off clean brief to Ricardo for any product-side actions needed |
| Day 14 | Both | End-of-week-2 review: all infrastructure confirmed ready. Align on Week 3 campaign launch date. | Brief Ricardo. Set expectations: first data in 48–72 hrs of launch. |

End of Week 2 — Deliverables

The following must be complete before any paid campaign activates:

| Deliverable | Owner | Deadline |
| --- | --- | --- |
| Funnel architecture document (full value ladder mapped) | Antonio | Day 3 |
| Brand alignment audit completed | Antonio | Day 4 |
| Creative brief: 3–5 ad angles with hooks | Antonio | Day 5 |
| AI for Chefs landing page copy | Antonio | Day 9 |
| OTO 1 and OTO 2 upsell page copy | Antonio | Day 11 |
| Email welcome sequence (5 emails) | Antonio | Day 12 |
| Meta Ads account audit report | Sean | Day 3 |
| Pixel + conversion events verified across all pages | Sean | Day 4 |
| Tracking stack: GA4 + UTM framework live | Sean | Day 5 |
| Meta Ads account restructured — campaigns ready to activate | Sean | Day 10 |
| End-to-end funnel test passed | Sean | Day 12 |
| Weekly performance reporting template live | Sean | Day 13 |
| Week 2 review presented to Ricardo | Both | Day 14 |

Brand Alignment Reference

Every asset produced in weeks 1 and 2 must pass against these non-negotiables before it goes to Ricardo or to market.

| Element | Use | Avoid |
| --- | --- | --- |
| Colour palette | Navy #1F2A44 ¦ Gold #C7A86D ¦ Beige #E6D9C3 ¦ Charcoal #333333 | Neon tones, bright colours, chaotic palettes |
| Typography | Playfair Display for headings ¦ Inter / Open Sans for body | Decorative fonts, inconsistent sizing |
| Tone | Direct, practical, authoritative. Educational value first. | Hype marketing, lifestyle angles, inspirational clichés, unrealistic promises |
| Ad creative | Founder-led video, carousel with practical lessons, clean static with strong headline | Guru-style ads, overstaged promos, dramatic food photography |
| Messaging angle | 'Understanding food cost is what turns a good cook into a valuable chef.' | Passion-based hooks, vague motivational copy, soft CTAs |
| Brand positioning | Professional executive academy — closer to business education than restaurant marketing | Lifestyle content, celebrity chef energy, casual kitchen aesthetic |

What Does Not Start in Weeks 1–2

These items are in scope for the engagement — they do not begin until infrastructure is confirmed clean and creative is approved.

- Paid Meta campaigns — no spend until pixel is verified and creative is approved

- Email send to existing list — audit the list first, confirm opt-in quality

- Cohort demand generation — begins week 3 once front-end funnel is live

- Academy module launch — Phase 2 of 90-day plan, post-cohort fill

Chef's Office Australia  |  Marketing & Growth Engagement  |  Phase 1  |  Confidential